## Sheet1
Task description | Subtasks | Start Date | Completion Date | Team | Curtis Wilson (Team Lead) | Abhang Sonawane | Benjamin Ng | Nayan Khodke | Neha Choudhari
Create Project Plan | create an initial project plan | 2014-02-08 | 2014-02-10 | [5 empty] | X
Create SRS | Project Definition, Scope High Level Requirements | 2014-02-08 | 2014-02-10 |  | X
| System Description | 2014-02-08 | 2014-02-10 |  |  |  | X
| Operational and Functional Requirements | 2014-02-08 | 2014-02-10 | [5 empty] | X
| Non-functional requirements, Outstanding Issues | 2014-02-08 | 2014-02-10 |  |  | X
| Behavioural Diagrams and Business Object Description | 2014-02-08 | 2014-02-10 |  |  |  |  | X
Create Class Diagram | define classes | 2014-02-10 | 2014-02-13 |  | X | X |  |  | X
| define methods | 2014-02-10 | 2014-02-13 |  | X | X | X |  | X
Create Intuitive User Interface | Design home screen | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
| Design rack CRUD screens | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
| Design mouse CRUD screens | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
| Design filtered search screen | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
| Design settings screen | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
| Design export to csv screen | 2014-02-15 | 2014-02-21 |  |  |  | X |  | X
Implement Intuitive User Interface | Implement home screen | 2014-02-22 | 2014-03-03 |  |  |  |  | x | X
| Implement rack CRUD screens | 2014-02-22 | 2014-03-06 |  |  | x |  |  | X
| Implement mouse CRUD screens | 2014-02-22 | 2014-03-10 |  | x
| Implement filtered search screen | 2014-02-22 | 2014-03-14 |  | x |  | x | x | X
| Implement settings screen | 2014-02-22 | 2014-03-20 |  |  |  |  | x
| Implement export to csv screen | 2014-02-22 | 2014-03-21 |  |  | x
Create Database Diagrams | create tables | 2014-03-06 | 2014-03-15 |  |  |  |  | X
| create relationships between tables | 2014-03-06 | 2014-03-17 |  |  |  |  | X
functional requirements | Req# 1-5 | 2014-03-10 | 2014-03-25 |  | X | X |  | X
| Req# 6-10 | 2014-03-10 | 2014-04-02 |  | X | X | X |  | X
| Req# 11-15 | 2014-03-10 | 2014-04-16 |  | X | X
non functional requirements |  | 2014-03-10 | 2014-04-16 |  | X | X | X | X | X
Create test plan | create test cases | 2014-04-01 | 2014-04-12 |  |  |  |  | X
| run test cases, log bugs | 2014-04-01 | 2014-04-16 |  |  |  | X |  | X
| fix bugs | 2014-04-01 | 2014-04-18 |  | X | X